## Sheet1
Risk | Risk Statement | Response Strategy | Objectives | Likelihood | Impact | Risk Level |  |  | Impact
Internet failure | Inability to connect to the internet due to various reasons would impact being able to complete the project. | Make sure internet connection is strong and stable, preferably wired or with the router nearby. Store important files and information locally so they can always be accessed. | Reduce likelihood of internet failure and potential impact. | Medium | Low | 2 |  |  | Low | Medium | High
Illness | Getting ill could mean missing vital development time and/or affecting productivity/compentence during development. | Don't leave lots of work till the last minute just in case illness strikes, make sure there is plenty of time to complete the project regardless. | Mitigate impact of illness. | Medium | Medium | 5 | Likelihood | Low | 1 | 4 | 7
Time mismanagement | Not managing time could mean not completing the project before the deadline and being forced to miss important features out, rush the whole project, or deliver it late. | Project planning and time allocation. | Reduce likelihood of time mismanagement. | Medium | High | 8 |  | Medium | 2 | 5 | 8
Failure to understand key concepts | Not understanding key concepts that are being worked with could lead to lots of errors or just generally poor work. | Take time to understand the training and refer to notes often. | Reduce likelihood of failure to understand key concepts. | Low | High | 7 |  | High | 3 | 6 | 9
Hardware failure | Hardward such as the computer or laptop that is being worked on, or the harddrive within the device, could fail leading to not being able to work on the project or even losing data/work done. | Check that hardware has no obvious issues before use. | Reduce likelihood of hardware failure. | Low | High | 7
Software issues | Software used during the development of the project could have glitches or unexpected errors, leading to not being able to work on a specific part of the project. | Make sure software is up to date. | Reduce likelihood of software issues. | Low | Medium | 5
Fire | Fire in the workplace could lead to loss of equipment and thus data, or health risks to developer. | Put in place fire prevention strategies to avoid a fire occurring in the first place. Additionally, have a fire extinguisher/blanket somewhere reachable. | Reduce likelihood of fire, and mitigate impact. | Low | High | 7
Database not secured | A poorly secured database could leave vulnerabilities leading to various attacks that could disrupt development or the working application e.g. SQL Injection. | Make SQL injection attacks more difficult to implement through refactoring code relating to the database. | Reduce likelihood of attacks | Low | High | 7